## Workplan Timeline
Cenla Mental Health Workforce Accelerator Program Grant |  |  |  | 2024 | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | Metrics Used to Track Progress (Goals) | Additional Notes
Task | Responsible / Accountable | Consulted | Informed | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Project and Partner Management
Calls with State Regional Chair(s) & National TA Provider | Regional Chair(s) | National Council | Rapides Foundation
Calls with placement sites | Regional Chair(s) | National Council | Rapides Foundation
Calls with other partners (e.g., Supervisors, Motivo and/or Triad) | Regional Chair(s) | National Council | Rapides Foundation
Calls with academic partners | Regional Chair(s) | National Council | Rapides Foundation
Infrastructure Build Out
Resources for key program implementation | National Council | Regional Chair(s) Other partners | Rapides Foundation
Develop standard operating procedures across key connection points | National Council | Regional Chair(s) Other partners | Rapides Foundation
Recruitment
Candidates | Placement Sites Regional Chair(s) | National Council | Rapides Foundation Placement Sites
Placement Sites | Regional Chair(s) | National Council | Rapides Foundation
Academic partners | Regional Chair(s) | National Council | Rapides Foundation Placement Sites
Other partners (e.g., Supervisors, Motivo and /or Triad) | Regional Chair(s) | National Council | Placement Sites
Application Processes - Placement Sites
Construct application/MOA/MOU | Regional Chair(s) | National Council | Rapides Foundation
Distribute placement site application | Regional Chair(s) | National Council | Rapides Foundation
Review applications | Regional Chair(s) | National Council | Rapides Foundation
Make site selections | Regional Chair(s) | National Council | Rapides Foundation
Execute MOA or MOU as appropriate | Regional Chair(s) | National Council | Rapides Foundation
Execute financial administration documentation | Regional Chair(s) | National Council | Rapides Foundation
Application Processes - Candidates
Construct application/MOA/MOU | Regional Chair(s) | National Council | Rapides Foundation
Distribute candidate application | Regional Chair(s) Other partners | National Council | Rapides Foundation
Support post-master candidates (should this go after make candidate selection?) | Regional Chair(s) | Placement Sites National Council | Rapides Foundation
Review applications | Placement Sites Regional Chair(s) | National Council Regional Chair(s) | Rapides Foundation
Make candidate selections | Placement Sites | National Council Regional Chair(s) | Rapides Foundation
Application Processes - Academic Partners
Construct partnership letter | Regional Chair(s) | National Council | Rapides Foundation
Distribute opportunity to academic partners | Regional Chair(s) | National Council | Rapides Foundation
Review interested academic partners | Regional Chair(s) | National Council | Rapides Foundation
Make academic partner decisions | Regional Chair(s) | National Council | Rapides Foundation
Execute partnership letter as appropriate | Regional Chair(s) | National Council | Rapides Foundation
Notify Selection of Interested Partners
Notify candidates | Placement Sites Regional Chair(s) | National Council | Rapides Foundation
Notify placement sites | Regional Chair(s) | National Council | Rapides Foundation
Notify academic partners | Regional Chair(s) | National Council | Rapides Foundation
Notify other partners | Regional Chair(s) | National Council | Rapides Foundation
Financial Administration
Financial contract execution (including annual renewals) -Placement Sites -Other (e.g., Supervision/Licensure partners) | Regional Chair(s) | Rapides Foundation | National Council
Payment schedules | Regional Chair(s) | Rapides Foundation | National Council
Billing mechanisms | Regional Chair(s) | Rapides Foundation | National Council
Processing/Issuing payments | Regional Chair(s) | Rapides Foundation | National Council
Monitoring budgets | Regional Chair(s) | Rapides Foundation | National Council
Onboarding - Placement Sites
Initial placement site onboarding | Regional Chair(s) | National Council | Rapides Foundation
Ongoing placement site onboarding of new organizations | Regional Chair(s) | National Council | Rapides Foundation
Onboarding - Candidates
Hold orientation | Regional Chair(s) | National Council | Rapides Foundation
Ongoing candidate onboarding and orientation | Regional Chair(s) | National Council | Rapides Foundation
Onboarding - Academic Partners
Ongoing academic partner onboarding and orientation | Regional Chair(s) | National Council | Rapides Foundation
Onboarding - Other Partners (Motivo, Triad, etc.)
Hold orientation | Regional Chair(s) | National Council | Rapides Foundation
Ongoing onboarding and orientation | Regional Chair(s) | National Council | Rapides Foundation
Training and Technical Assistance (skill development and capacity building)
Working with placement sites | Regional Chair(s) | National Council | Rapides Foundation
Working with candidates | Regional Chair(s) | National Council | Rapides Foundation
Working with academic partners | Regional Chair(s) | National Council | Rapides Foundation
Supervision supports | Partners Regional Chair(s) | National Council Regional Chair(s) | Rapides Foundation
Licensure supports | Partners Regional Chair(s) | National Council Regional Chair(s) | Rapides Foundation
Evaluation and Performance Monitoring
Develop data collection tools and processes | Regional Chair(s) | National Council Rapides Foundation | Placement Sites Academic Partners Other Partners
Collect data from candidates, placement sites, academic partners, and other partners | Regional Chair(s) | National Council Rapides Foundation | Placement Sites Academic Partners Other Partners Rapides Foundation
Analyze data & impact assessment | Regional Chair(s) | National Council Rapides Foundation | Placement Sites Academic Partners Other Partners
Develop Monthly Progress reports | Regional Chair(s) | National Council Rapides Foundation | Placement Sites Academic Partners Other Partners
Utilize findings to make program adjustments | National Council Regional Chair(s) | Rapides Foundation | Placement Sites Academic Partners Other Partners
Ongoing Marketing and Communication
Disseminate program information | National Council Regional Chair(s) | Rapides Foundation | n/a

## Plan of Work
Cenla Mental Health Workforce Accelerator Program Grant |  |  |  | Plan of Work
Task | Responsible / Accountable | Consulted | Informed
Project and Partner Management
Calls with State Regional Chair(s) & National TA Provider | Regional Chair(s) | National Council | Rapides Foundation
Calls with placement sites | Regional Chair(s) | National Council | Rapides Foundation
Calls with other partners (e.g., Supervisors, Motivo and/or Triad) | Regional Chair(s) | National Council | Rapides Foundation
Calls with academic partners | Regional Chair(s) | National Council | Rapides Foundation
Infrastructure Build Out
Resources for key program implementation | National Council | Regional Chair(s) Other partners | Rapides Foundation
Develop standard operating procedures across key connection points | National Council | Regional Chair(s) Other partners | Rapides Foundation
Recruitment
Candidates | Placement Sites Regional Chair(s) | National Council | Rapides Foundation Placement Sites
Placement Sites | Regional Chair(s) | National Council | Rapides Foundation
Academic partners | Regional Chair(s) | National Council | Rapides Foundation Placement Sites
Other partners (e.g., Supervisors, Motivo and /or Triad) | Regional Chair(s) | National Council | Placement Sites
Application Processes - Placement Sites
Construct application/MOA/MOU | Regional Chair(s) | National Council | Rapides Foundation
Distribute placement site application | Regional Chair(s) | National Council | Rapides Foundation
Review applications | Regional Chair(s) | National Council | Rapides Foundation
Make site selections | Regional Chair(s) | National Council | Rapides Foundation
Execute MOA or MOU as appropriate | Regional Chair(s) | National Council | Rapides Foundation
Execute financial administration documentation | Regional Chair(s) | National Council | Rapides Foundation
Application Processes - Candidates
Construct application/MOA/MOU | Regional Chair(s) | National Council | Rapides Foundation
Distribute candidate application | Regional Chair(s) Other parnters | National Council | Rapides Foundation
Support post-master candidates (should this go after make candidate selection?) | Regional Chair(s) | Placement Sites National Council | Rapides Foundation
Review applications | Placement Sites Regional Chair(s) | National Council Regional Chair(s) | Rapides Foundation
Make candidate selections | Placement Sites | National Council Regional Chair(s) | Rapides Foundation
Application Processes - Academic Partners
Construct partnership letter | Regional Chair(s) | National Council | Rapides Foundation
Distribute opportunity to academic partners | Regional Chair(s) | National Council | Rapides Foundation
Review interested academic partners | Regional Chair(s) | National Council | Rapides Foundation
Make academic partner decisions | Regional Chair(s) | National Council | Rapides Foundation
Execute partnership letter as appropriate | Regional Chair(s) | National Council | Rapides Foundation
Notify Selection of Interested Partners
Notify candidates | Placement Sites Regional Chair(s) | National Council | Rapides Foundation
Notify placement sites | Regional Chair(s) | National Council | Rapides Foundation
Notify academic partners | Regional Chair(s) | National Council | Rapides Foundation
Notify other partners | Regional Chair(s) | National Council | Rapides Foundation
Financial Administration
Financial contract execution (including annual renewals) -Placement Sites -Other (e.g., Supervision/Licensure partners) | Regional Chair(s) | Rapides Foundation | National Council
Payment schedules | Regional Chair(s) | Rapides Foundation | National Council
Billing mechanisms | Regional Chair(s) | Rapides Foundation | National Council
Processing/Issuing payments | Regional Chair(s) | Rapides Foundation | National Council
Monitoring budgets | Regional Chair(s) | Rapides Foundation | National Council
Onboarding - Placement Sites
Initial placement site onboarding | Regional Chair(s) | National Council | Rapides Foundation
Ongoing placement site onboarding of new organizations | Regional Chair(s) | National Council | Rapides Foundation
Onboarding - Candidates
Hold orientation | Regional Chair(s) | National Council | Rapides Foundation
Ongoing candidate onboarding and orientation | Regional Chair(s) | National Council | Rapides Foundation
Onboarding - Academic Partners
Ongoing academic partner onboarding and orientation | Regional Chair(s) | National Council | Rapides Foundation
Onboarding - Other Partners (Motivo, Triad, etc.)
Hold orientation | Regional Chair(s) | National Council | Rapides Foundation
Ongoing onboarding and orientation | Regional Chair(s) | National Council | Rapides Foundation
Training and Technical Assistance (skill development and capacity building)
Working with placement sites | Regional Chair(s) | National Council | Rapides Foundation
Working with candidates | Regional Chair(s) | National Council | Rapides Foundation
Working with academic partners | Regional Chair(s) | National Council | Rapides Foundation
Supervision supports | Partners Regional Chair(s) | National Council Regional Chair(s) | Rapides Foundation
Licensure supports | Partners Regional Chair(s) | National Council Regional Chair(s) | Rapides Foundation
Evaluation and Performance Monitoring
Develop data collection tools and processes | Regional Chair(s) | National Council Rapides Foundation | Placement Sites Academic Partners Other Partners
Collect data from candidates, placement sites, academic partners, and other partners | Regional Chair(s) | National Council Rapides Foundation | Placement Sites Academic Partners Other Partners Rapides Foundation
Analyze data & impact assessment | Regional Chair(s) | National Council Rapides Foundation | Placement Sites Academic Partners Other Partners
Develop Monthly Progress reports | Regional Chair(s) | National Council Rapides Foundation | Placement Sites Academic Partners Other Partners
Utilize findings to make program adjustments | National Council Regional Chair(s) | Rapides Foundation | Placement Sites Academic Partners Other Partners
Ongoing Marketing and Communication
Disseminate program information | National Council Regional Chair(s) | Rapides Foundation | n/a